## Estimation & Cost
PartnerAPI – Public API Programme for a Travel Booking Company
Estimation & Cost Analysis
A. Project & Cost Assumptions
Working days per week | 5
Launch target (weeks) | 10
Working hours per day | 8
Assumed blended engineering rate | 2000 | per hour
B. PERT Three-Point Estimation
Activity | Optimistic (O) | Most Likely (M) | Pessimistic (P) | PERT Expected Time (TE) | Hours | Estimated Cost | Scope
API Design | 4 | 6 | 10 | 6.3333 | 0 | 0 | Baseline
Booking Endpoints | 10 | 14 | 24 | 15 | 0 | 0 | Baseline
Sandbox | 4 | 6 | 12 | 6.6667 | 0 | 0 | Baseline
Documentation | 3 | 5 | 8 | 5.1667 | 0 | 0 | Baseline
Partner Onboarding | 5 | 8 | 15 | 8.6667 | 0 | 0 | Baseline
Baseline Total |  |  |  | 41.84 | 334.72 | 669440
C. VERIFIED NUMERIC RESULTS
API Design | 6.33
Booking Endpoints | 15
Sandbox | 6.67
Documentation | 5.17
Partner Onboarding | 8.67
Baseline Total | 41.84
Baseline Duration (weeks) | 8.37
Target (weeks) | 10
Schedule Margin (weeks) | 1.63
D. Baseline Schedule Check
Baseline effort (days) | 41.84
Baseline duration (weeks) | 8.37
Target (weeks) | 10
Target (days) | 50
Margin (days) | 8.16
Margin (weeks) | 1.63
Status | FITS WITHIN 10-WEEK TARGET
E. Custom Request Impact
Item | Days | Hours | Cost
Custom Request 1 | 12 | 96 | 192000
Custom Request 2 | 18 | 144 | 288000
Combined | 30 | 240 | 480000
F. Full Scope Impact
Baseline | 41.84
Custom requests | 30
Full scope (days) | 71.84
Full scope duration (weeks) | 14.37
Delay (weeks) | 4.37
G. Commercial Cost Summary
Baseline development cost | 669440
Custom-request cost | 480000
Full-scope development cost | 1149440
Illustrative GST – baseline (18%) | 120499.2
Illustrative baseline total incl. GST | 789939.2
Illustrative GST – full scope (18%) | 206899.2
Illustrative full-scope total incl. GST | 1356339.2
* Illustrative only – actual tax treatment must be confirmed.
H. Cost by Activity
API Design | 50.64 | 101280
Booking Endpoints | 120 | 240000
Sandbox | 53.36 | 106720
Documentation | 41.36 | 82720
Partner Onboarding | 69.36 | 138720
9. Assumptions / Notes
- PERT estimates are planning estimates.
- They are not delivery guarantees.
- The O/M/P values are taken directly from the project brief.
- 5 working days = 1 working week.
- 8 hours/day is assumed for cost conversion.
- ₹2,000/hour is an assumed blended engineering rate.
- Custom requests are additional scope.
- Custom requests should preferably be handled through formal change control / Phase 2.
- Real commercial pricing would also consider: cloud infrastructure, API gateway, monitoring, hotel inventory/provider fees, security testing, production support, maintenance, and applicable taxes.

## PERT Reference
PERT Reference
O | Optimistic
M | Most Likely
P | Pessimistic
TE | Expected Time
Formula: | TE = (O + 4M + P) / 6
API Design Example: | (4 + 4*6 + 10) / 6 = 6.33 days